## Sheet1
RISK | CATEGORY | COMPONENT | PROBABILITY | IMPACT | RMMM(RISK MANAGEMENT, MITIGATION, MONITORING) | RE
Team member absent | Project, technical | Performance, schedule | 50% | 2 | constant communication with all group members, independent segments that could be worked on alternatively | 1
scarcity of resources(software tools) | Project, technical | Cost, preformance, schedule | 40% | 2 | proper earch and purchase of all software tools before implementation, Purchase and use of free and available software | 0.8
Low value of Product in the market | Business | Support | 70% | 3 | Good and constant monitoring of the market, provision of new features to boost product viability | 2.1
Time frame too short | Project | Schedule, performance | 40% | 2 | Proper planning using gant charts, ignoring of non-value adding features | 0.8
Compromising of design | Project, technical | Performance, Support | 60% | 2 | Proper reassesment at every phase, correction @ the design level and all other level that may have been affected | 1.2
registering a non-genuine company | Business | Performance | 60% | 2 | Proper monitoring of legal documents tendered by companies using info from the appropriate agencies, instant removal from the site | 1.2
Sudden growth of requirements | Project, technical | Schedule, performance | 40% | 1 | Stringent approach of following initial documentation, adjustment of the documents to be in sync with the project | 0.4
Procedural risk( Conflicting priorities, lack of clarity of responsibilities, improper process implementation) | Project, technical | Cost, preformance, schedule | 50% | 2 | Use of scheduled meetings to remind ourselves of our individual tasks, immediate correction of team member | 1
Risk of procastination | Project | Performance, schedule | 60% | 1 | Proper use of the gant chart provided at start time, team members would have to work for more hours | 0.6